## Ark1
Progress:
| Who does what: | What to do: | When: | Deadline: | Solved: | Why not solved:
| Denis | Make downpayment for an agreement | 2018-02-12
| Dag | Apply to Tynset planning office to abtain land an plot coordinates | 2018-02-12
| Dag | Run a noise audit on site | 2018-02-12 | 2018-03-02
| Denis | Provide electrical design of the container for review | 2018-02-12 |  |  | Must be translated to Norwegian
| Jan Inge, Dag, Jonny | Site preparation offer - removal of trees from tronfjell Maskin | 2018-02-16
| Jan Inge, Dag, Jonny | Fence installation offer from Tronfjell Maskin | 2018-02-16 |  |  | Not sure if the offered fence is the right type for the site (does not block noise)
| Jan Inge, Dag, Jonny | Basement offer from Tronfjell Maskin | 2018-02-16
| Jonny | Agree with Eidsiva scheduele and iniate a process to deliver optical line to the site in Alvdal | 2018-02-16
| Dag | Agree with Tynset planing office on construction phases | 2018-02-19
| Dag | Apply for bulding permit for site preperation, fence installation, basement construction and small office building | 2018-02-19
| Ivar, Jonny | Design electrical scheme to connect container to transformator | 2018-03-01
| Ivar, Jonny | Design earthing for container | 2018-03-01
| Denis, Jonny | Choose an company for site surveillance and alarm system | 2018-03-01
| Dag | Apply for bulding permit for "noisy" containers | 2018-03-05
| Dag | Provide timetable for the project | 2018-03-16
| Dag | Provide budget for fence, parking, small office and basement for container | 2018-03-16
| Denis, Dag, Jonny | Provide exact place where transformers will be set - Denis, Dag, Jonny - prerequisites - land plot coordinates received from Tynset planning office Install cables and transformers - NOK - prerequisites - land plot planing done | unknown