Referat:

Møte mellom Nord-Østerdal Elektroservice AS og Fjell IT AS i forbindelse med prosjekt Datasenter på Plassen.
Tilstede: Ivar Eggestad, Mads Kjølhaug og Jonny Andersen			Dato 13.03-2018

Punkter som ble diskutert.

- Fjell IT provides translated schematics for the electrical in the containers.

- Fjell IT supplies plot map in DWG format.

- Fjell IT supplies invoice information.

- Fjell IT checks if there is need for lightning protection.

- Fjell IT checks if there is any need for any kind of security clearance for any of the workers.

- NØES will inform Tronfjell Maskin on where the cables will be on the plot.

- NØES have 1 – 2 weeks delivery time for cables and light pylons.

- NØES gives a suggestion for where to put up the light pylons.

- NØES have no contract with Dataroom AS.

- NØES must hire another company to terminate fiber.

- NØES will send an invoice every 14 day on used time and equipment.

- NØES send their hourly rate to Fjell IT, and Fjell IT forwards it to Denis.

- NØES have planned with 2 – 4 persons on the project + some extra help.

- NØES begins with earthing as soon as they have the electrical schematics.

- NØES makes an agreement with Tronfjell Maskin on who supplies the ducts for the cables.