## Ark1
Data center in Alvdal
Time schedule - Project
Pr: 2018-04-11
Job | From | To | Responsible | Status/comments
Application for the project | 22.02.2018 | 02.03.2018 | Norconsult | Permit approved
Application to start removing forest, groundwork and basement | 02.03.2018 | 05.03.2018 | Norconsult | Permit approved
Remove three frome the plot | 05.03.2018 | 13.03.2018 | Tronfjell Maskin
Remove the top vegetation | 13.03.2018 | 06.04.2018 | Tronfjell Maskin
Application for approval from the Labor Inspection Authority | 15.03.2018 |  | Norconsult | Sent in 15.03.2018. Rejected 23.03.2018. Statement of deficiencies submitted XX.04.2018
Application to place the containers and the office building | 21.03.2018 |  | Norconsult | We need the permit from Labor Inspection before the commune can give the permit for the office building
Support layer for the basement to container and trafo (four pcs) | 06.04.2018 | 16.04.2018 | Tronfjell Maskin
Basement for the transformers and placement of the transformers (four pcs) | 01.04.2018 | 20.04.2018 | NØK | First transformers supplies power to 25.04.2018
Basement for the first containers | 16.04.2018 | 25.04.2018 | Tronfjell Maskin
Electrical cables from transformator to the containers - Ready for conection | 25.04.2018 | 31.04.2018 | Elektroservice
Trench for water and drain incl. pipes and tank | 25.04.2018 | 31.04.2018 | Tronfjell Maskin
Support layer for the office building, parking and rest of the road/area | 10.04.2018 | 20.05.2018 | Tronfjell Maskin | See each activity for when spesific area have to been finished
Place the first container | 05.05.2018 | 06.05.2018 | NMC/Tronfjell Maskin
Montage inside the first container | 06.05.2018 | 10.05.2018 | NMC/Fjell IT
Place the modules for the office building | 2018-05-10 | 2018-05-16 | Tronfjell Maskin
Connection of water and drainage to the building | 2018-05-15 | 2018-05-16 | Tronfjell Maskin
Electrical cables from the transformator to the office building and connection to the modules | 2018-05-15 | 2018-05-16 | Elektroservice
Basement for the three next containers | 15.05.2018 | 25.05.2018 | Tronfjell Maskin
Place the next three containers | 01.06.2018 | 02.06.2018 | NMC/Tronfjell Maskin
Montage inside the containers | 02.06.2018 | 06.06.2018 | NMC/Fjell IT
Fence around the containers | 10.05.2018 | 15.05.2018 | Tronfjell Maskin
Monitoring system | 15.05.2018 | 25.05.2018 | Fjell IT/Elektroservice
Application for to use the office building and the first four containers | 2018-05-05 | 2018-05-17 | Norconsult | The application can be sent in 14 days before the works are finished, but we will not get the permit before its finished.
Basement for the last four transformers and placement of the transformers | Summer/autumn 2018 |  | NØK
Basement for the last four containers | Summer/autumn 2018 |  | Tronfjell Maskin
Place the four last containers | Summer/autumn 2018
Application for to use the last four containers | Summer/autumn 2018 |  | Norconsult