Date 21.04.2018

Norconsult have spoken with the labour Office, but they haven`t had time to look at our application

Uploaded offers/suggestions from Tronfjell Maskin:

- Fence

- Top cover on the plot

- Pipes for water and sewage

Uploaded photos of the plot.

Got information that we might be choosing containers that don`t need a foundation. Awaiting your decision.

Was supposed to get an offer for storage this week, but didn`t receive it.

Norconsult had a budget meeting with Tronfjell Maskin

Still waiting for the budget and progress plan from Norconsult.

Got an offer from Norconsult regarding some of the documentation that Dataroom AS should have as the builder. It was in Norwegian, asked them to translate it in to English.

Got a forwarded email from Arild regarding the application to the labour Office and the containers. Sent an explanation of this to Denis.